## 0 Summary
HANA RESIDENCE – QUOTATION AUDIT R3 (client answers applied, 11 Oct 2026)
Quotation 261015 Grand Total after R3 | 1043267.62
Sheet total before R3 edits | 971295.16
Net change R3 (see sheet 2) | 71972.46
Est. gross margin R3 (sheet 3, excl. Porter commission) | ≈27.0% (≈29.6% excl. smart home)
A. Still missing – Priority A | 99590
B. Still missing – Priority B | 44750.42
C. Optional – Priority C | 8300
Revised total – R3 + A | 1142857.62
Revised total – R3 + A + B | 1187608.04
Backups: 'Hana Sheon & Tee - BACKUP R1 (09 Oct)' and 'Hana Sheon & Tee - BACKUP R2 (11 Oct)' (state just before R3 edits).

## 1 Missing Items
# | Section | Item to add | Qty | Unit | Suggested sell rate (RM) | Amount (RM) | Why / where seen | Priority
1 | Curtains | Curtains & blinds – section now RM0 (sheer 34 ft has no rate; all other rooms deleted after R2). R1/R2 had RM16,280: sheer 34ft@160, kitchen blinds, double-layer Parents/Master/Son, roman WIC/Daughter, laundry/maid blinds | 1 | L/S | 16280 | 16280 | If curtains are now by another vendor, add 'Curtains by owner' to Exclusions instead. Do not leave a priced line at RM0. | A
2 | Preliminaries | Floor / lift / staircase protection (removed from sheet after R2, was RM2,500) | 1 | L/S | 2500 | 2500 | Protection of retained tiles in Son's & Daughter's bathrooms, existing staircase & glass balustrade (kept) is now more important, not less. | A
3 | Wet Works | PC Sum – tile MATERIAL: Powder, Master Bath, FF/Parents Bath, Entrance, Laundry floor+wall, Wet Kitchen wall, Terraces (approx. 2,500 sqft incl. 10% wastage @ PC RM12/sqft) | 2500 | sqft | 12 | 30000 | Quote still says 'TBC upon final selection' = RM0. Reduced from 3,600 sqft because Son's & Daughter's bathrooms keep existing tiles; terrace 315 sqft added. | A
4 | Wet Works | Laundry wall tiles – Dong Peng Limestone JH12352GZ 600x1200 structured (labour) | 180 | sqft | 35 | 6300 | GF legend red wall-tile lines along laundry walls. 3D laundry shows full-height wall tile. | A
5 | Wet Works | Wet kitchen wall tile – quantity top-up (take-off ~330 vs 250 sqft) | 80 | sqft | 35 | 2800 |  | B
6 | Wet Works | Staircase risers & nosing (Porter covers treads only) – PC sum | 1 | L/S | 3500 | 3500 | Still open with Porter. | A
7 | Wet Works | Removal of existing timber flooring 1,647 sqft – now written into Demolition L/S description at no extra cost | 1647 | sqft | 2.86 | 4710.42 | Confirm the demolition subcon's RM37,145 covers it. If not, cost ~RM2/sqft -> sell RM2.86 (+RM4.7k). | B
8 | Ceiling | Ceiling quantity top-up (corridor & stair, powder, utility, maid + under-measured master, WIC, son, daughter) | 1000 | sqft | 6 | 6000 | Quote bedroom ceiling 2,799 sqft vs rough take-off ~3,800. | B
9 | Ceiling | Moisture-resistant ceiling – Parents Bath & Powder | 70 | sqft | 7 | 490 | Son's & Daughter's done in R3. | A
10 | Ceiling | AC grille cut-out / access panels (only if ducted / cassette units chosen) | 10 | nos | 150 | 1500 | Aircond now quoted as wall-mounted PS – confirm type. | C
11 | Ceiling | Curved arch / curved wall-to-ceiling transition at staircase & corridor | 2 | nos | 1200 | 2400 | 3D p.4-7, p.37. | B
12 | Preliminaries | Scaffolding for double-volume void | 1 | L/S | 3500 | 3500 | Living/dining void ~6-7 m. | A
13 | Preliminaries | Final chemical cleaning, approx. 5,500 sqft | 1 | L/S | 3800 | 3800 |  | A
14 | Preliminaries | Contractor All-Risk insurance | 1 | L/S | 2500 | 2500 | Optional. | C
15 | Joinery | Foyer / Living divider c/w planter box & concealed lighting | 1 | nos | 8500 | 8500 | 3D p.8-12, plan label 'DIVIDER'. | A
16 | Joinery | Second hidden door @ Utility / Powder | 1 | nos | 4500 | 4500 | Plan labels 'HIDDEN DOOR' x2. | A
17 | Joinery | Maid room tatami platform c/w storage | 1 | nos | 2800 | 2800 |  | B
18 | Joinery | Parents Bath – floating vanity + tall storage cabinet | 1 | L/S | 6000 | 6000 | 3D p.43. Depends on 'First Floor Bathroom' = Parents Bath. | A
19 | Joinery | Parents Bath – mirror cabinet c/w LED | 1 | nos | 1200 | 1200 | Son's & Daughter's done in R3. | A
20 | Joinery | Powder room – vanity / stone basin base & mirror | 1 | L/S | 3000 | 3000 | 3D p.44. | B
21 | Joinery | Staircase side wall – full-height V-groove panelling | 1 | L/S | 8500 | 8500 | 3D p.37-38. | B
22 | Joinery | Master Bath – open-shelf tall storage | 1 | nos | 3500 | 3500 |  | C
23 | Table Top | Dry Kitchen island top-up for 900 deep + waterfall ends | 1 | L/S | 3400 | 3400 |  | A
24 | Table Top | Parents Bath vanity top + open hole | 1 | L/S | 1270 | 1270 | 4 ft @ 280 + 1 hole @ 150. | A
25 | Doors & Windows | 10mm tempered glass shower screen – Parents Bath | 1 | nos | 1800 | 1800 | Son's & Daughter's keep existing. | A
26 | Doors & Windows | Existing doors – refurbish / laminate c/w new black lever handles (~10 leaves) | 10 | nos | 650 | 6500 |  | B
27 | Electrical | 32A dedicated point for induction hob (hob by owner, point by Groo) | 1 | nos | 650 | 650 |  | A
28 | Electrical | Additional 15A points – water heaters, dishwasher, wine chiller | 4 | nos | 350 | 1400 |  | A
29 | Electrical | PROVISIONAL – DB upgrade / sub-DB (smart home + aircond + heavy appliances) | 1 | L/S | 4500 | 4500 | Aircond now in scope -> load increases. | A
30 | Electrical | Aircond power points – top-up to match 6 units in PS (4 quoted) | 2 | nos | 300 | 600 |  | B
31 | Electrical | LED step-light points @ staircase | 10 | nos | 160 | 1600 |  | B
32 | Electrical | Exhaust fan points – powder & bathrooms | 4 | nos | 200 | 800 |  | C
33 | Plumbing | PROVISIONAL – piping re-route for new vanity positions (Parents, Son's, Daughter's) | 3 | nos | 1200 | 3600 | New vanity cabinets may not match existing inlet/outlet positions. | B
34 | Curtains | Family Area – full-height sheer + night curtain | 14 | ft | 160 | 2240 | 3D p.41-44. | B
TOTAL – Priority A
TOTAL – Priority B
TOTAL – Priority C
TOTAL – all

## 2 R3 Changes
Section | Change | Before | After | Δ RM
Header | F6 date | 10/8/2026 | 08 Oct 2026 | 0
Header | J8 company address | 143 Jln Desa Utama, Taman Danau Desa | Level 3A, Wisma JAG, Jalan Desa Utama, Taman Desa, 58100 KL | 0
1.0 Ceiling | Son's & Daughter's Bathroom – dismantle + 9mm MR ceiling c/w access panel (new rows 84-85) | - | 162 sqft @ RM9 | 1458
2.0 Painting | Ceiling paint qty now includes bathroom ceiling | 2,799 | 2,961 sqft | 162
3.0 Wet Works | Son's Bathroom tiling, floor trap, mitre – deleted (tiles remain) | 15,324.14 | 0 | -15324.14
3.0 Wet Works | Daughter's Bathroom tiling, floor trap, mitre – deleted (tiles remain) | 14,407.72 | 0 | -14407.72
3.0 Wet Works | Terrace 1, 2 & 3 – outdoor anti-slip tiles c/w screed to fall, waterproofing, ponding test (labour; tile material TBC) | - | 315 sqft @ RM45 (cost 31.5/0.7) | 14175
3.0 Wet Works | Screed -> cement screed + self-levelling for glue-down (Porter 20-yr warranty) | 1,647 @ RM5 | 1,647 @ RM8 | 4941
3.0 Wet Works | Demolition L/S description – adds removal of existing timber flooring; bathroom scope changed (amount unchanged) | 53,064.29 | 53,064.29 | 0
4.0 Plumbing | Water heater installation @ Master & First Floor Bath (heater by owner) | - | 2 @ RM250 | 500
4.0 Plumbing | Descriptions: sinks/taps/appliances & water heaters by owner; bathroom reinstall line covers basin re-fix to new vanity | - | - | 0
7.0 Doors & Windows | Wet Kitchen Option 2 – hack & enlarge sink-wall window c/w new black alu window | - | L/S RM4,500 | 4500
8.0 Joinery | Son's & Daughter's Bath – floating vanity sink cabinet x2 + mirror cabinet c/w LED x2 | - | 2 @ 2,600 + 2 @ 1,200 | 7600
8.0 Joinery | Master Bedroom – TV wall reworded to Option 2 (twin round columns + low fireplace plinth) | 13,500 | 13,500 | 0
9.0 Table Top | Son's & Daughter's vanity top 6 ft @ 280 + 2 more open holes | - | 1,680 + 300 | 1980
12.0 Smart Home | 15% markup on all 5 lines; supplier name removed from client note | 142,588.80 | 163,977.12 | 21388.32
13.0 Air-Cond | PROVISIONAL SUM – 6 inverter wall-mounted units c/w piping @ RM5,000 | Not included | 30,000 | 30000
14.0 Landscape | PROVISIONAL SUM – front garden & terraces | - | 15,000 | 15000
Exclusions | New block under Grand Total: loose furniture, appliances, sanitary, taps & sinks, water heaters, decorative lights, fireplace, artwork; gate; JMB deposit/permits | - | - | 0
Payment terms | Smart Home billed separately: 50% deposit / 40% delivery / 10% T&C | - | - | 0
NET CHANGE

## 3 Margin Estimate
Section | Quoted (RM) | Est. cost (RM) | Gross profit (RM) | GP %
Preliminaries | 2100 | 1500
1.0 Ceiling | 38659 | 27100
2.0 Painting | 24761 | 17100
3.0 Demolition & Masonry / Wet Works | 247447.5 | 176850
4.0 Plumbing | 9850 | 6850
5.0 Electrical | 37470 | 25000
6.0 Light Fittings & Fans | 2100 | 1500
7.0 Doors & Windows | 17400 | 12700
8.0 Joinery | 339250 | 215000
9.0 Table Top | 23120 | 16400
10.0 Flooring (Porter, incl. staircase) | 82233 | 76259
11.0 Curtains & Blinds | 0 | 0
12.0 Smart Home (15%) | 163977.12 | 142588.8
13.0 Air-Cond (PS) | 30000 | 25500
14.0 Landscape (PS) | 15000 | 12000
Project Management | 9900 | 5000
TOTAL
TOTAL excl. Smart Home
Est. cost from QS Pricing Matrix ranges + supplier quotes (Dong Peng, Porter, M Vida). Excludes Porter's 10% designer commission (~RM6.4k, off-quote). Aircond / landscape costs assume ~15-20% on PS.

## 4 Rate Flags
Section | Item | Est. margin | Target | Comment | Priority
Project Management | PM fee RM1.80/sqft = RM9,900 | ~0.9% of RM1.04M | Min 3% (~RM31k) | Now also coordinating aircond, landscape & smart home vendors. | A
Flooring | Porter S&I RM39/sqft | ~6% + 10% commission | 25% | Thin but low-risk. Negotiate install RM4.5. | B
Flooring | Staircase steps RM18,000 | ~11% + commission | 25% | Risers & nosing still excluded. | B
Ceiling | 9mm plaster RM6/sqft, L-box RM28/ft | 17-40% | 45% | Matrix sell RM10 / RM50. | B
Wet Works | Decimal rates (37.14, 53,064.29, 45.00 ...) | 30% | - | Decimals reveal cost ÷ 0.7. Round before sending. | B
Air-Cond | PS 6 units @ RM5,000 | ~15% assumed | 15-20% | Replace with real supplier quote + layout (units, HP, wall vs cassette/ducted). | A
Landscape | PS RM15,000 | ~20% assumed | 20-25% | Replace with landscape subcon quote once scope agreed. | A
Wet Works | Self-levelling RM8/sqft | ~35% | 30% | Porter quoted self-levelling RM3-4 + screed. OK. | C

## 5 Questions
Status | Question | Answer | Action in sheet
Answered | Son's & Daughter's bathrooms | Keep tiles; only mirror cabinet + sink cabinet + ceiling redo | Applied (tiling deleted, ceiling/joinery/table top added)
Answered | Maid Bath | No works | Nothing in quote – OK
Answered | Terraces after decking removal | Tiles floor | Applied – 315 sqft labour; material in tile PC (Missing #3)
Answered | Existing glass balustrade | Keep | Balustrade removed from missing list; protection added to Missing #2
Answered | Wet Kitchen / Master Bedroom option | Wet Kitchen Opt 2, Master Bedroom Opt 2 | Applied – see OPEN #3 on Wet Kitchen Opt 2 reading
Answered | Sinks/taps, hood/hob/oven, water heaters, fireplace | Owner | Applied – exclusions + install labour only
Answered | Smart home | Groo quotes it in | Applied – 15% markup (+RM21,388.32)
Answered | Unit size | 5,500 sqft | Kept
Answered | Company address | Changed | Applied – J8
Answered | Quote date | 8 Oct | Applied – '08 Oct 2026'
Answered | Design fee | Billed separately, done | No change
Answered | Smart-home deposit | Most likely follow | Applied – 50/40/10 line under payment terms
Answered | Exclusions | Aircond & landscape quoted in; others by owner; no gate; JMB deposit by owner | Applied – sections 13 & 14 (PS) + Exclusions block
OPEN | 1. 'First Floor Bathroom' (RM13,419) – FF only has Master, Son's, Daughter's. Is it the Parents Bath (GF)? |  | If yes rename + add Parents Bath joinery/top/screen (Missing #18-19, #24-25)
OPEN | 2. Existing wood floor -> dismantle + self-levelling (applied, 20-yr warranty). Reply to Porter & confirm demolition subcon covers removal. |  | Revert: row 114 RM8 -> RM5 (-RM4,941)
OPEN | 3. Wet Kitchen Opt 2 read from 3D p.33 as: larger black-frame window at sink wall, rest same as Opt 1 (curved island, reeded sliding doors kept). |  | If Opt 2 also drops island / sliding doors -> deduct rows 180, 212, Table Top 268
OPEN | 4. Curtains section RM0 + protection removed after R2 – intentional? |  | Missing #1-2 (RM18,780)
OPEN | 5. Aircond: no. of units, wall-mounted vs cassette/ducted, brand. |  | Replace PS
OPEN | 6. Landscape scope / designer. |  | Replace PS
OPEN | 7. Foyer finish: Ling Hua Bai (Dong Peng count) vs Bellezza (DWG legend).
OPEN | 8. Porter: area breakdown of 1,647 sqft (drawing ~1,880) + staircase risers/nosing price.

## 6 Supplier Quotes
Supplier | Date | Item | Cost (RM) | Quoted to client | Notes
Dong Peng (DP Ceramic) | 09/10/2026 | Ling Hua Bai 900x1800x9 honed, 91 pcs @ RM250 | 22750 | 30,030 (91 @ RM330) | Logistics TBC, unloading excl., 50% deposit, 12-wk production
Porter Rosewood | 09/10/2026 | Art Deco E30 straight plank 1,647 sqft | 51200 | 64,233 incl. install | Incl. 10% designer commission; area breakdown TBC
Porter Rosewood (installer est.) | 10/10/2026 | Glue-down install 1,647 sqft @ RM5.5 | 9059 | (in RM39/sqft) | 20-yr warranty only on self-levelled cement / tile
Porter Rosewood | 09/10/2026 | Staircase steps 1.2mm + install RM3k | 16000 | 18,000 | Steps only
M Vida (AETHO) | 13/09/2026 | Smart home package | 142588.8 | 163,977.12 (15%) | 3-month lead time; 50/40/10 to client
Aircond – TBC | - | 6 units PS |  | 30,000 PS | Get quote
Landscape – TBC | - | PS |  | 15,000 PS | Get quote