## 0 Summary
HANA RESIDENCE – QUOTATION AUDIT R1 (vs 3D Proposal R1 + DWG 01-02/10/2026)
Current draft quotation 261015 (Grand Total) | 980113.34
Est. gross margin of current draft (see sheet 4) | ≈27.5% (≈32% excl. smart home)
A. Missing items – Priority A (clearly in 3D/drawings) | 139124.28
B. Missing items – Priority B (very likely, confirm) | 74320
C. Missing items – Priority C (optional/provisional) | 6800
D. Smart home 15% markup (recommended) | 21388.32
E. Ling Hua Bai over-measure you may need to remove (labour + material) | -46939.4
F. 'First Floor Bathroom' if it's a phantom (not Parents Bath) | -13419.16
Revised total – A + D + E (minimum fix) | 1093686.54
Revised total – A + B + D + E | 1168006.54
How to read: the draft adds up correctly, but (1) ~RM43k of tile material is unpriced, (2) Parents Bath / staircase / divider / bathroom joinery are missing, (3) wood & ceiling are under-measured, (4) Ling Hua Bai is over-measured by ~800 sqft, (5) smart home carries 0% margin. Rates are my suggested SELL prices at ~35% GP – replace with real subcon quotes.

## 1 Missing Items
# | Section | Item to add | Qty | Unit | Suggested sell rate (RM) | Amount (RM) | Why / where seen | Priority
1 | Wet Works | PC Sum – tile MATERIAL for bathrooms x4 + powder, foyer, laundry floor/wall, wet kitchen wall (approx. 3,600 sqft incl. 10% wastage @ PC RM12/sqft, adjust upon final selection) | 3600 | sqft | 12 | 43200 | Quote says 'TBC upon final selection' = currently RM0. Only Ling Hua Bai 900x1800 material is priced. Without a PC sum the client reads it as included. | A
2 | Wet Works | Laundry wall tiles – Dong Peng Limestone JH12352GZ 600x1200 structured (labour, prime coat, C2TE-S1, grout) | 180 | sqft | 35 | 6300 | New Layout GF legend: red wall-tile lines along laundry walls (4310 + 2290). 3D laundry shows full-height wall tile. Not in quote. | A
3 | Wet Works | Wet kitchen wall tile – quantity top-up (take-off ~330 sqft vs 250 quoted) | 80 | sqft | 35 | 2800 | Red wall lines 4670 + 5050 + 2118 mm x ~3.0 m height less openings. | B
4 | Wet Works | Parents Bath – hack, Mapei 223 waterproofing + 72h ponding test, floor & wall tiling 750x1500 | 280 | sqft | 35 | 9800 | 3D p.42 Parent's Bath fully redone. Quote has no Parents Bath. CHECK: if the 'First Floor Bathroom' line was meant to be Parents Bath, rename it instead of adding. | A
5 | Wet Works | Parents Bath – 6" floor trap | 2 | nos | 137.14 | 274.28 | As other bathrooms. | A
6 | Wet Works | Staircase – treads & risers finish (timber-look cladding / matching tile) c/w nosing, approx. 20 steps | 20 | step | 380 | 7600 | Demolition Plan GF hatches the staircase red (to be hacked). 3D p.37-38 shows new warm timber-look stair. Nothing in quote. | A
7 | Wet Works | Terrace 1, 2 & 3 – new floor finish after removal of existing wood decking (approx. 315 sqft) | 315 | sqft | 28 | 8820 | Demolition line says 'remove ... wood decking' but no reinstatement. Confirm finish with client (outdoor tile / composite decking). | B
8 | Ceiling | Ceiling quantity top-up: FF corridor & stair, powder, utility, maid room, + under-measured rooms (master, WIC, son, daughter) | 1000 | sqft | 6 | 6000 | Quote ceiling total 2,799 sqft. Rough take-off: Master ~410 (quoted 300), WIC ~320 (190), Son ~310 (180), Daughter ~280 (130), Corridor ~215 (0). If partial ceiling intended, write 'partial' in description. | B
9 | Ceiling | Moisture-resistant ceiling – Parents, Son's & Daughter's bathrooms, powder room | 140 | sqft | 7 | 980 | Only Master Bath has ceiling. 3D shows LED pelmet ceilings in all bathrooms. | A
10 | Ceiling | Air-cond linear grille cut-out / access panel 600x600 | 10 | nos | 150 | 1500 | 3D shows linear diffusers (living, dining, family area, master) – ducted AC needs openings & access panels even if AC is by owner's vendor. | B
11 | Ceiling | Curved arch / curved wall-to-ceiling transition at staircase & corridor | 2 | nos | 1200 | 2400 | 3D p.4-7, p.37 curved arch openings. | B
12 | Preliminaries | Scaffolding for double-volume void (ceiling, painting, curtain track & pendant installation) | 1 | L/S | 3500 | 3500 | Living/dining void approx. 6-7 m height. Ceiling and painting rates assume normal height. | A
13 | Preliminaries | Final chemical cleaning, approx. 5,700 sqft built-up | 1 | L/S | 3800 | 3800 | Not in quote. QS matrix: post-reno cleaning RM600-1,200 for condo → landed 5,700 sqft scale up. | A
14 | Preliminaries | Contractor All-Risk insurance (approx. 0.25% of contract) | 1 | L/S | 2500 | 2500 | Optional but recommended for RM1M job. | C
15 | Joinery | Foyer / Living divider – full-height framed screen c/w indoor planter box, pebbles & concealed lighting | 1 | nos | 8500 | 8500 | 3D p.8-12 & plan label 'DIVIDER'. Not in quote. | A
16 | Joinery | Second hidden door (flush with wall panelling, concealed hinges & push latch) @ Utility / Powder | 1 | nos | 4500 | 4500 | 3D plan labels 'HIDDEN DOOR' x2. Quote only covers the Dry Kitchen one. | A
17 | Joinery | Maid room tatami platform c/w storage | 1 | nos | 2800 | 2800 | Plan label 'TATAMI W/ STORAGE' at maid room. Quote has wardrobe + headboard only. | B
18 | Joinery | Parents Bath – floating vanity cabinet | 1 | nos | 2800 | 2800 | 3D p.43. | A
19 | Joinery | Parents Bath – tall storage cabinet (dark fluted door) | 1 | nos | 3200 | 3200 | 3D p.43 right side. | A
20 | Joinery | Son's & Daughter's Bath – floating vanity cabinet | 2 | nos | 2600 | 5200 | 3D p.73, p.78. | A
21 | Joinery | Parents, Son's & Daughter's Bath – mirror cabinet c/w LED | 3 | nos | 1200 | 3600 | 3D shows mirror cabinets in all three. | A
22 | Joinery | Powder room – vanity / stone pedestal basin base & mirror | 1 | L/S | 3000 | 3000 | 3D p.44. | B
23 | Joinery | Staircase side wall – full-height V-groove feature panelling | 1 | L/S | 8500 | 8500 | 3D p.37-38. Confirm extent with YS. | B
24 | Joinery | Master Bath – open-shelf tall storage unit | 1 | nos | 3500 | 3500 | 3D master bath (right side timber shelving). | C
25 | Table Top | Dry Kitchen island – top-up for 900mm depth + waterfall ends (≈44 sqft sintered @ RM140/sqft vs 10ft x RM280 quoted) | 1 | L/S | 3400 | 3400 | Per-ft rate assumes 600mm depth. Island is 2800x900 with thick waterfall/curved end in 3D. | A
26 | Table Top | Vanity tops – Parents, Son's, Daughter's bath (sintered / quartz) | 12 | ft | 280 | 3360 | 3 vanities x ~4 ft. | A
27 | Table Top | Open hole – additional basins | 3 | nos | 150 | 450 |  | A
28 | Doors & Windows | 10mm tempered glass shower screen – Parents, Son's & Daughter's bath | 3 | nos | 1800 | 5400 | Only Master Bath screen quoted. 3D shows glass screens in all. | A
29 | Doors & Windows | Existing doors – refurbish / laminate to match new palette c/w new black lever handles (approx. 10 leaves) | 10 | nos | 650 | 6500 | 3D shows flush doors with black handles everywhere. No door painting/refurb in Painting either. Confirm door schedule. | B
30 | Doors & Windows | Glass balustrade (12mm laminated tempered) c/w timber handrail @ staircase & void edge – IF replacing existing | 46 | ft | 450 | 20700 | 3D p.38-42 frameless glass + timber rail. Confirm whether existing balustrade stays. | B
31 | Electrical | 32A dedicated point for induction hob (from DB) | 1 | nos | 650 | 650 | Induction hob cannot run on 15A. | A
32 | Electrical | Additional 15A points – water heaters x4, dishwasher, wine chiller (quote has only 6 nos) | 6 | nos | 350 | 2100 | 4 bathrooms with rain showers + oven + dryer + dishwasher + wine chiller = ~12 heavy points. | A
33 | Electrical | PROVISIONAL – DB upgrade / new sub-DB for smart home & added load (replace 'TBC') | 1 | L/S | 4500 | 4500 | KNX + 18 curtain motors + cinema + heavy appliances. 'TBC' = RM0 today. | B
34 | Electrical | LED step-light points @ staircase | 10 | nos | 160 | 1600 | 3D p.38. | B
35 | Electrical | Exhaust fan points – powder room & bathrooms | 4 | nos | 200 | 800 |  | C
36 | Plumbing | Water heater installation labour (unit by owner) | 4 | nos | 180 | 720 |  | A
37 | Plumbing | PROVISIONAL – concealed piping re-route for new vanity positions @ Parents, Son's, Daughter's bath | 3 | nos | 1200 | 3600 | Quote assumes 'reinstall' only. 3D vanity/shower positions differ from existing. | B
38 | Flooring | Engineering wood – quantity top-up (rough take-off ~1,880 sqft vs 1,230 quoted) | 650 | sqft | 22 | 14300 | FF wood rooms ≈ 165 m² + Parents Room ≈ 20 m². Verify in CAD before sending. | A
39 | Flooring | Levelling screed – quantity top-up to match | 650 | sqft | 5 | 3250 |  | A
40 | Flooring | Skirting – quantity top-up | 200 | ft | 8 | 1600 |  | B
41 | Curtains | Family Area – full-height sheer + night curtain (over-height) | 14 | ft | 160 | 2240 | 3D p.41-44 sheer curtains. Not in quote. | A
TOTAL – Priority A
TOTAL – Priority B
TOTAL – Priority C
TOTAL – all

## 2 Qty Check
Section | Item | Quoted qty | My take-off | Unit | Rate | Diff (RM) | Note
Wet Works | Ling Hua Bai 900x1800 floor tiling (labour) | 2000 | 1190 | sqft | 37.14 | -30083.4 | Living+Dining+Breakfast ≈ 6.44 m x 13.2 m + living extension ≈ 86.5 m² (931 sqft) + Wet Kitchen 4.42 x 5.40 = 257 sqft. Over by ~810 sqft.
Wet Works | Ling Hua Bai material (pcs, 17.44 sqft/pc) | 139.2 | 79 | pcs | 280 | -16856 | 1,190 sqft x 1.15 wastage / 17.44 = 79 pcs. Over by ~60 pcs.
Wet Works | Wet kitchen wall tile | 250 | 330 | sqft | 35 | 2800 | Under – see Missing Items #3.
Wet Works | 'First Floor Bathroom' tiling (331 sqft + traps + mitre) | 331 | 0 | sqft | 35 | -11585 | New FF layout has only Master, Son's & Daughter's bath (Bath 3 becomes Walk-in Closet). Probably meant Parents Bath (GF) – rename, don't double count.
Flooring | Engineering wood | 1230 | 1880 | sqft | 22 | 14300 | Under – see Missing Items.
Ceiling | Total plaster ceiling | 2799 | 3800 | sqft | 6 | 6006 | Under – see Missing Items.
Preliminaries | Rorobin 6 trips | 6 | 0 | trip | 350 | -2100 | Demolition L/S already says 'incl. Rorobin disposal'. Either remove here or reword as 'additional trips for joinery/packaging waste'.
Wet Works | 45° mitre corner – unit shown as 'inch' | 251 | 251 | inch→ft? | 37.14 | 0 | RM37/inch would be wrong. Change unit label to 'ft' so the client doesn't challenge it.

## 3 Rate & Margin
Section | Item | Quoted rate | Subcon cost (QS matrix) | Est. margin | Target | Comment | Priority
Smart Home | AETHO / M Vida package | 142,588.80 | 142,588.80 | 0% | 15-20% | Passed through at vendor price – zero margin on 14.5% of contract, while Groo carries coordination, 3-month lead time, KNX programming risk. Add 15% (≈+RM21.4k) or let client contract AETHO directly + charge 8-10% coordination. | A
Project Management | PM fee RM1.80/sqft | 9,900 | - | ~1% of contract | 5-8% (guide) | RM9,900 on a RM1M, 6-month, 2-storey job with 10+ trades is thin. Suggest min 3% (~RM29k). | A
Ceiling | 9mm plaster ceiling RM6/sqft | 6.00 | 3.60-5.00 | 17-40% | 45% | Matrix selling RM10. Move to RM7.50-8.00 (+RM4-6k). | B
Ceiling | L-box LED RM28/ft | 28.00 | 18-25 | 11-36% | 45% | Matrix selling RM50. Move to RM40. | B
Curtains | Double-layer curtain RM135/ft | 135.00 | 86-120 | 11-36% | 25-35% | Night 55-75 + day 28-42 + track 3. Move to RM150-160. | B
Joinery | WIC wardrobe w/ black-frame glass doors RM991/ft | 991/ft | 750-900/ft? | 9-24% | 33% | Alu-frame glass doors + LED cost more than melamine doors. Get carpenter price before sending. | B
Flooring | Engineering wood RM22/sqft | 22.00 | 14-20 (est.) | 10-35% | 25% | Porter Rosewood 15-20mm – confirm supplier price incl. underlay & wastage. | B
Wet Works | Rates like 37.14 / 53,064.29 / 12,285.71 / 137.14 | - | - | 30% (cost/0.7) | - | Decimals show the client you priced cost ÷ 0.7. Round to 38.00, 53,100, 12,300, 140.00. | B
Joinery | Kitchen wall cabinet with lift-up doors RM537/ft | 537/ft | 170-260 + lift-up fittings | ~30% | 33% | Blum Aventos ~RM400-600 each. OK if hardware counted, else thin. | C

## 4 Margin Estimate
Section | Quoted (RM) | Est. cost (RM) | Gross profit (RM) | GP %
Preliminaries | 4600 | 3000
1.0 Ceiling | 37201 | 26000
2.0 Painting | 24599 | 17000
3.0 Demolition & Masonry / Wet Works | 298314.54 | 212000
4.0 Plumbing | 9350 | 6500
5.0 Electrical | 37470 | 25000
6.0 Light Fittings & Fans | 2100 | 1500
7.0 Doors & Windows | 12900 | 9500
8.0 Joinery | 331650 | 210000
9.0 Table Top | 21140 | 15000
10.0 Flooring | 32020 | 25000
11.0 Curtains & Blinds | 16280 | 12000
12.0 Smart Home | 142588.8 | 142588.8
Project Management | 9900 | 5000
TOTAL
TOTAL excl. Smart Home
Est. cost = my estimate from the QS Pricing Matrix subcon ranges, not actual supplier quotes. Replace with real subcon quotes as they come in.

## 5 Drawing Issues
Type | Issue | Action | Priority
Title block | GF sheets (ORI / DEMOLISHED / NEW LAYOUT PLAN-G) copyright says 'property of seb design studio'. | Fix before sending – it's another firm's name. FF sheets are already correct. | A
Title block | All 3 GF sheets titled 'FURNITURE LAYOUT PLAN (GROUND FLOOR)' regardless of content; Drawing No. blank on all 6 sheets; every sheet labelled 'ID 01'. | Number them e.g. HR-ID-01…, title per content. | A
Title block | 'PROJECT TITILE' typo; dates 02/10 (GF) vs 1/10 (FF); drawn by YANXIANG vs YS. | Align. | C
Plot | GF Demolished Layout Plan is rotated 90° and clipped – Breakfast/Dining left side and Parents Room are cut off the sheet. | Re-plot to fit A3. | A
Scale | Every sheet 'NOT TO SCALE'. | Plot at 1:100 on A3 so contractors (and we) can measure off the PDF. | B
Content | GF New Layout has no wall legend (new wall / wall to hack / hidden doors / divider). | Add as per FF legend; the kitchen–dining wall is hacked in the demolition plan. | A
Content | FF Demolition Plan doesn't mark Son's (Bath 2) & Daughter's (Bath 1) bathrooms for hacking, but the 3D and the quote redo them. | Decide scope: if redoing, add hatch; if not, remove from quote (≈RM29.7k tiling + plumbing). | A
Content | Wet Kitchen Option 1 (curved island + glass sliding doors) vs Option 2 – quote only prices Option 1. | Show Option 2 as an alternative / deduction line so client sees the choice. | B
Content | Master Bedroom Opt 2 (twin columns) – quote merges into TV divider. | Confirm which option. | C
Missing sheet | Reflected Ceiling Plan GF & FF (levels, coves, Ø coffers, pelmets, AC grilles, access panels). | Drives Ceiling qty (≈RM37-50k). | A
Missing sheet | Lighting layout (coordinate AETHO: 118 downlights, tracks, linear, 246 m strip, pendants, wall lights). | Drives electrical points + smart home scope. | A
Missing sheet | Power & data point layout (13A, 15A, 32A, data, TV, AC isolator, fireplace, curtain motors). | Drives Electrical qty. | A
Missing sheet | Plumbing layout (inlet/outlet, floor trap, heater, island sink, laundry). |  | B
Missing sheet | Floor finishes plan with area schedule (sqft per finish). | Locks flooring & tile quantities. | A
Missing sheet | Wall finishes plan + bathroom / wet kitchen tile elevations. | Locks wall tile quantities. | B
Missing sheet | Cabinetry elevations & sections per item (W x D x H, materials, hardware). | Basis for the W/D/H columns in quote and for carpenter pricing. | A
Missing sheet | Door & window schedule (new / hidden / refurbish / sealed). |  | B
Missing sheet | Staircase & balustrade detail. |  | B
Missing sheet | Curtain & blind schedule (location, type, width, height, motorised). |  | C

## 6 Questions
For | Question
Client | Son's & Daughter's bathrooms – full redo (as 3D) or keep existing tiles?
Client | Maid Bath – any works? (Not in 3D, not in quote.)
Client | Terraces – what finish after decking removal?
Client | Existing glass balustrade at void/stair – keep or replace?
Client | Wet Kitchen Option 1 or 2? Master Bedroom option 1 or 2?
Client | Who supplies kitchen sinks/taps, hood/hob/oven, water heaters, fireplace unit?
Client | Smart home – contract through Groo (with markup) or directly with AETHO?
Internal | Unit size: quote uses 5,500 sqft, fee proposal says 5,745 sqft – which is correct?
Internal | Company address: quote header '143 Jln Desa Utama, Taman Danau Desa' vs fee proposal 'Level 3A, Wisma JAG, Taman Desa'.
Internal | Quote date shows '10/8/2026' – print as '08 Oct 2026' to avoid being read as 10 Aug.
Internal | Is the design fee (Fee Proposal 261026) billed separately? Quote has no design fee line.
Internal | Payment terms: AETHO likely needs ~50% upfront for imported items – add a separate smart-home deposit so Groo isn't funding it.
Internal | Add an explicit EXCLUSIONS block: aircond, loose furniture, appliances, sanitary ware, decorative lights, fireplace, artwork/plants, landscape/turfing, gate, permits & JMB deposits.